## Change 2
CSc 190 PROJECT SCHEDULE - BASELINE SCHEDULE |  |  |  | TEAM NAME: | jBehaving
Submitted date: 04/29/14 |  |  |  | Submitted by: | Bai Xiong
(Tuesday's class)
Only indicate changes!
| PROJECT WORK PHASES: | Baseline Start Date | Baseline Finish Date | New Baseline Start Date | New Baseline Finish Date | Completed (Yes / No)
| Project CHARTER | 2014-02-19 | 2014-03-19 |  |  | Yes | ✔ | No
| PMP | 2014-03-05 | 2014-04-02 |  |  | Yes | ✔ | No
| Feature Wireframes | 2014-03-19 | 2014-04-02 | 2014-03-19 | 2014-05-08 | Yes |  | No
| SRS | 2014-03-12 | 2014-04-30 | 2014-03-19 | 2014-05-08 | Yes |  | No
| Req'ts Meeting | 2014-04-30 | 2014-05-07 | 2014-05-01 | 2014-05-11 | Yes |  | No
| Arch. Design |  |  |  |  | Yes |  | No
| Feature Wireframes |  |  |  |  | Yes |  | No
| SDS |  |  |  |  | Yes |  | No
| Baseline Code (Design, Code, Integrate & Test ) |  |  |  |  | Yes |  | No
| Feature 1 |  |  |  |  | Yes |  | No
| Feature 2 |  |  |  |  | Yes |  | No
| Feature 3 |  |  |  |  | Yes |  | No
| Feature 4 |  |  |  |  | Yes |  | No
| Feature 5 |  |  |  |  | Yes |  | No
| STS |  |  |  |  | Yes |  | No
| System Testing & STR |  |  |  |  | Yes |  | No
| UM |  |  |  |  | Yes |  | No
| Delivery Meeting |  |  |  |  | Yes |  | No
Reason for the change: |  | Tasks left to be completed by SRS and Wireframes were increased from requirements meeting.

## Change1
CSc 190 PROJECT SCHEDULE - BASELINE SCHEDULE |  |  |  | TEAM NAME: | jBehaving
Submitted date: 04/01/14 |  |  |  | Submitted by: | Cody Lanier
(Tuesday's class)
Only indicate changes!
| PROJECT WORK PHASES: | Baseline Start Date | Baseline Finish Date | New Baseline Start Date | New Baseline Finish Date | Completed (Yes / No)
| Project CHARTER | 2014-02-19 | 2014-03-19 |  |  | Yes | No
| PMP | 2014-03-05 | 2014-04-02 |  |  | Yes | No
| Feature Wireframes | 2014-03-19 | 2014-04-02 | 2014-03-19 | 2014-04-30 | Yes | No
| SRS | 2014-03-12 | 2014-04-30 | 2014-03-19 | 2014-04-30 | Yes | No
| Req'ts Meeting | 2014-04-30 | 2014-05-07 |  |  | Yes | No
| Arch. Design |  |  |  |  | Yes | No
| Feature Wireframes |  |  |  |  | Yes | No
| SDS |  |  |  |  | Yes | No
| Baseline Code (Design, Code, Integrate & Test ) |  |  |  |  | Yes | No
| Feature 1 |  |  |  |  | Yes | No
| Feature 2 |  |  |  |  | Yes | No
| Feature 3 |  |  |  |  | Yes | No
| Feature 4 |  |  |  |  | Yes | No
| Feature 5 |  |  |  |  | Yes | No
| STS |  |  |  |  | Yes | No
| System Testing & STR |  |  |  |  | Yes | No
| UM |  |  |  |  | Yes | No
| Delivery Meeting |  |  |  |  | Yes | No
Reason for the change: |  | No need to rush the wireframes and we started the SRS one week later than expected

## Original
CSc 190 PROJECT SCHEDULE - BASELINE SCHEDULE |  |  |  | TEAM NAME: | jBehaving
Submitted date: 03/18/14 |  |  |  | Submitted by: | Cody Lanier
(Tuesday's class)
Only indicate changes!
| PROJECT WORK PHASES: | Baseline Start Date | Baseline Finish Date | New Baseline Start Date | New Baseline Finish Date | Completed (Yes / No)
| Project CHARTER | 2014-02-19 | 2014-03-19 |  |  | Yes | No
| PMP | 2014-03-05 | 2014-04-02 |  |  | Yes | No
| Feature Wireframes | 2014-03-19 | 2014-04-02 |  |  | Yes | No
| SRS | 2014-03-12 | 2014-04-30 |  |  | Yes | No
| Req'ts Meeting | 2014-04-30 | 2014-05-07 |  |  | Yes | No
| Arch. Design |  |  |  |  | Yes | No
| Feature Wireframes |  |  |  |  | Yes | No
| SDS |  |  |  |  | Yes | No
| Baseline Code (Design, Code, Integrate & Test ) |  |  |  |  | Yes | No
| Feature 1 |  |  |  |  | Yes | No
| Feature 2 |  |  |  |  | Yes | No
| Feature 3 |  |  |  |  | Yes | No
| Feature 4 |  |  |  |  | Yes | No
| Feature 5 |  |  |  |  | Yes | No
| STS |  |  |  |  | Yes | No
| System Testing & STR |  |  |  |  | Yes | No
| UM |  |  |  |  | Yes | No
| Delivery Meeting |  |  |  |  | Yes | No
Reason for the change: