## 190 timesheet
CSc 190 WEEKLY TIME and STATUS REPORT | [5 empty] | TEAM NAME: JBehaving
Submitted date: 4/8/14 | [5 empty] | Submitted by: Michel Watson
(Tuesday's class)
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | TOTAL for the Week
1 | Ashley Finger | 4.75 | 0 | 0 | 0 | 0 | 2 | 0 | 6.75
2 | Bai Xiong | 3.5 | 0 | 0 | 0 | 5 | 0.25 | 0 | 8.75
3 | Cody Lanier | 4 | 0 | 0 | 0.25 | 0 | 1 | 0 | 5.25
4 | Cody Prior | 2.75 | 0 | 0 | 0.5 | 0 | 1.25 | 0 | 4.5
5 | Daniel Gallegos | 2.75 | 0 | 0 | 0 | 0 | 2 | 0 | 4.75
6 | Michel Watson | 1.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 2
WEEKLY TOTAL (hrs) |  | 19.25 | 0 | 0 | 0.75 | 5 | 7 | 0 | 32
PERCENT COMPLETE |  |  |  | 100% | 99% | 50% | 10% | 0%
*Record times to nearest 15 minutes, representing less than one-hour increments as .25, .50, or .75.
ACCUMULATED TIME SPENT BY EACH TEAM MEMBER: | [9 empty] | Percent of Semester Total
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | SEMESTER TOTAL
1 | Ashley Finger | 20.5 | 0.5 | 10.5 | 9.5 | 0 | 2 | 0 | 43 | 18.98%
2 | Bai Xiong | 23.25 | 0.5 | 7 | 8.5 | 5.5 | 0.75 | 0 | 45.5 | 20.09%
3 | Cody Lanier | 24 | 0.5 | 6.25 | 8.5 | 0 | 1.75 | 0 | 41 | 18.1%
4 | Cody Prior | 16.75 | 0.5 | 3.25 | 8 | 0 | 1.25 | 0 | 29.75 | 13.13%
5 | Daniel Gallegos | 19 | 1 | 5.5 | 6 | 0 | 2.5 | 0 | 34 | 15.01%
6 | Michel Watson | 17.75 | 0.5 | 7.5 | 6 | 0 | 1.5 | 0 | 33.25 | 14.68%
SEMESTER TOTAL (hrs) |  | 121.25 | 3.5 | 40 | 46.5 | 5.5 | 9.75 | 0 | 226.5 | 100%