## 190 timesheet
CSc 190 WEEKLY TIME and STATUS REPORT | [5 empty] | TEAM NAME: JBehaving
Submitted date: 4/22/14 | [5 empty] | Submitted by: Michel Watson
(Tuesday's class)
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | TOTAL for the Week
1 | Ashley Finger | 2.25 | 0 | 0 | 0 | 0 | 3.5 | 0 | 5.75
2 | Bai Xiong | 4 | 0 | 0 | 0 | 0 | 1.75 | 0 | 5.75
3 | Cody Lanier | 1.5 | 0 | 0 | 0 | 0 | 4 | 0 | 5.5
4 | Cody Prior | 1.5 | 0 | 0 | 0 | 0 | 2 | 0 | 3.5
5 | Daniel Gallegos | 2.25 | 0.5 | 0 | 0 | 0 | 4 | 0 | 6.75
6 | Michel Watson | 2.25 | 0 | 0 | 0 | 0 | 2.5 | 0 | 4.75
WEEKLY TOTAL (hrs) |  | 0 | 0.5 | 0 | 0 | 0 | 17.75 | 0 | 32
PERCENT COMPLETE |  |  |  | 100% | 100% | 75% | 45% | 0%
*Record times to nearest 15 minutes, representing less than one-hour increments as .25, .50, or .75.
ACCUMULATED TIME SPENT BY EACH TEAM MEMBER: | [9 empty] | Percent of Semester Total
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | SEMESTER TOTAL
1 | Ashley Finger | 25.25 | 0.5 | 10.5 | 9.5 | 0 | 9.5 | 0 | 55.25 | 19.1%
2 | Bai Xiong | 30 | 0.5 | 7 | 8.5 | 5.5 | 6 | 0 | 57.5 | 19.88%
3 | Cody Lanier | 27.25 | 0.5 | 6.25 | 8.5 | 0 | 8.25 | 0 | 50.75 | 17.55%
4 | Cody Prior | 20 | 0.5 | 3.25 | 8 | 0 | 6 | 0 | 37.75 | 13.05%
5 | Daniel Gallegos | 22 | 1.5 | 5.5 | 6 | 0 | 9.5 | 0 | 44.5 | 15.38%
6 | Michel Watson | 22.75 | 0.5 | 7.5 | 6 | 0 | 6.75 | 0 | 43.5 | 15.04%
SEMESTER TOTAL (hrs) |  | 147.25 | 4 | 40 | 46.5 | 5.5 | 46 | 0 | 289.25 | 100%