## 190 timesheet
CSc 190 WEEKLY TIME and STATUS REPORT | [5 empty] | TEAM NAME: JBehaving
Submitted date: 4/29/14 | [5 empty] | Submitted by: Michel Watson
(Tuesday's class)
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | TOTAL for the Week
1 | Ashley Finger | 5.5 | 0 | 0 | 0 | 0 | 7 | 0 | 12.5
2 | Bai Xiong | 5.5 | 0 | 0 | 0 | 1 | 8.25 | 0 | 14.75
3 | Cody Lanier | 4.5 | 0 | 0 | 0 | 0 | 17.5 | 0 | 22
4 | Cody Prior | 4.75 | 0 | 0 | 0 | 0 | 4.5 | 0 | 9.25
5 | Daniel Gallegos | 5 | 0 | 0 | 0 | 0 | 11 | 0 | 16
6 | Michel Watson | 5.5 | 0 | 0 | 0 | 0 | 8.25 | 0 | 13.75
WEEKLY TOTAL (hrs) |  | 0 | 0 | 0 | 0 | 1 | 56.5 | 0 | 88.25
PERCENT COMPLETE |  |  |  | 100% | 100% | 95% | 80% | 0%
*Record times to nearest 15 minutes, representing less than one-hour increments as .25, .50, or .75.
ACCUMULATED TIME SPENT BY EACH TEAM MEMBER: | [9 empty] | Percent of Semester Total
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | SEMESTER TOTAL
1 | Ashley Finger | 30.75 | 0.5 | 10.5 | 9.5 | 0 | 16.5 | 0 | 67.75 | 17.95%
2 | Bai Xiong | 35.5 | 0.5 | 7 | 8.5 | 6.5 | 14.25 | 0 | 72.25 | 19.14%
3 | Cody Lanier | 31.75 | 0.5 | 6.25 | 8.5 | 0 | 25.75 | 0 | 72.75 | 19.27%
4 | Cody Prior | 24.75 | 0.5 | 3.25 | 8 | 0 | 10.5 | 0 | 47 | 12.45%
5 | Daniel Gallegos | 27 | 1.5 | 5.5 | 6 | 0 | 20.5 | 0 | 60.5 | 16.03%
6 | Michel Watson | 28.25 | 0.5 | 7.5 | 6 | 0 | 15 | 0 | 57.25 | 15.17%
SEMESTER TOTAL (hrs) |  | 178 | 4 | 40 | 46.5 | 6.5 | 102.5 | 0 | 377.5 | 100%