## 190 timesheet
CSc 190 WEEKLY TIME and STATUS REPORT | [5 empty] | TEAM NAME: JBehaving
Submitted date: 5/6/14 | [5 empty] | Submitted by: Michel Watson
(Tuesday's class)
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | TOTAL for the Week
1 | Ashley Finger | 3 | 0 | 0 | 0 | 0 | 8.5 | 0 | 11.5
2 | Bai Xiong | 0.75 | 0 | 0 | 0 | 0 | 5.75 | 0 | 6.5
3 | Cody Lanier | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 1.5
4 | Cody Prior | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
5 | Daniel Gallegos | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 4
6 | Michel Watson | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 | 5.5
WEEKLY TOTAL (hrs) |  | 10.25 | 0 | 0 | 0 | 0 | 20.75 | 0 | 31
PERCENT COMPLETE |  |  |  | 100% | 100% | 99% | 99% | 0%
*Record times to nearest 15 minutes, representing less than one-hour increments as .25, .50, or .75.
ACCUMULATED TIME SPENT BY EACH TEAM MEMBER: | [9 empty] | Percent of Semester Total
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | SEMESTER TOTAL
1 | Ashley Finger | 33.75 | 0.5 | 10.5 | 9.5 | 0 | 25 | 0 | 79.25 | 19.4%
2 | Bai Xiong | 36.25 | 0.5 | 7 | 8.5 | 6.5 | 20 | 0 | 78.75 | 19.28%
3 | Cody Lanier | 31.75 | 0.5 | 6.25 | 8.5 | 0 | 27.25 | 0 | 74.25 | 18.18%
4 | Cody Prior | 26.75 | 0.5 | 3.25 | 8 | 0 | 10.5 | 0 | 49 | 12%
5 | Daniel Gallegos | 29 | 1.5 | 5.5 | 6 | 0 | 22.5 | 0 | 64.5 | 15.79%
6 | Michel Watson | 30.75 | 0.5 | 7.5 | 6 | 0 | 18 | 0 | 62.75 | 15.36%
SEMESTER TOTAL (hrs) |  | 188.25 | 4 | 40 | 46.5 | 6.5 | 123.25 | 0 | 408.5 | 100%