## 190 timesheet
CSc 190 WEEKLY TIME and STATUS REPORT | [5 empty] | TEAM NAME: JBehaving
Submitted date: 4/15/14 | [5 empty] | Submitted by: Michel Watson
(Tuesday's class)
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | TOTAL for the Week
1 | Ashley Finger | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 | 6.5
2 | Bai Xiong | 2.75 | 0 | 0 | 0 | 0 | 3.5 | 0 | 6.25
3 | Cody Lanier | 1.75 | 0 | 0 | 0 | 0 | 2.5 | 0 | 4.25
4 | Cody Prior | 1.75 | 0 | 0 | 0 | 0 | 2.75 | 0 | 4.5
5 | Daniel Gallegos | 1.75 | 0 | 0 | 0 | 0 | 3 | 0 | 4.75
6 | Michel Watson | 2.75 | 0 | 0 | 0 | 0 | 2.75 | 0 | 5.5
WEEKLY TOTAL (hrs) |  | 13.25 | 0 | 0 | 0 | 0 | 18.5 | 0 | 31.75
PERCENT COMPLETE |  |  |  | 100% | 100% | 75% | 33% | 0%
*Record times to nearest 15 minutes, representing less than one-hour increments as .25, .50, or .75.
ACCUMULATED TIME SPENT BY EACH TEAM MEMBER: | [9 empty] | Percent of Semester Total
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | SEMESTER TOTAL
1 | Ashley Finger | 23 | 0.5 | 10.5 | 9.5 | 0 | 6 | 0 | 49.5 | 19.24%
2 | Bai Xiong | 26 | 0.5 | 7 | 8.5 | 5.5 | 4.25 | 0 | 51.75 | 20.12%
3 | Cody Lanier | 25.75 | 0.5 | 6.25 | 8.5 | 0 | 4.25 | 0 | 45.25 | 17.59%
4 | Cody Prior | 18.5 | 0.5 | 3.25 | 8 | 0 | 4 | 0 | 34.25 | 13.31%
5 | Daniel Gallegos | 19.75 | 1 | 5.5 | 6 | 0 | 5.5 | 0 | 37.75 | 14.67%
6 | Michel Watson | 20.5 | 0.5 | 7.5 | 6 | 0 | 4.25 | 0 | 38.75 | 15.06%
SEMESTER TOTAL (hrs) |  | 133.5 | 3.5 | 40 | 46.5 | 5.5 | 28.25 | 0 | 257.25 | 100%