## 190 timesheet
CSc 190 WEEKLY TIME and STATUS REPORT | [5 empty] | TEAM NAME_____JBehaving___________________________
Submitted date:__2/25/14_______ | [5 empty] | Submitted by: __Michel Watson_____________________
(Tuesday's class)
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | TOTAL for the Week
1 | Ashley Finger | 1.5 | 0.5 | 1.5 | 0 | 0 | 0 | 0 | 3.5
2 | Bai Xiong | 4.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 7
3 | Cody Lanier | 4.5 | 0.5 | 2.25 | 0 | 0 | 0 | 0 | 7.25
4 | Cody Prior | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 2
5 | Daniel Gallegos | 3 | 0.5 | 0 | 0 | 0 | 0 | 0 | 3.5
6 | Michel Watson | 2.5 | 0.5 | 1.25 | 0 | 0 | 0 | 0 | 4.25
WEEKLY TOTAL (hrs) |  | 17.5 | 2.5 | 7.5 | 0 | 0 | 0 | 0 | 27.5
PERCENT COMPLETE |  |  |  | 25% | 0% | 0% | 0% | 0%
*Record times to nearest 15 minutes, representing less than one-hour increments as .25, .50, or .75.
ACCUMULATED TIME SPENT BY EACH TEAM MEMBER: | [9 empty] | Percent of Semester Total
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | SEMESTER TOTAL
1 | Ashley Finger | 1.5 | 0.5 | 1.5 |  |  |  |  | 3.5 | 12.73%
2 | Bai Xiong | 4.5 | 0 | 2.5 |  |  |  |  | 7 | 25.45%
3 | Cody Lanier | 4.5 | 0.5 | 2.25 |  |  |  |  | 7.25 | 26.36%
4 | Cody Prior | 1.5 | 0.5 | 0 |  |  |  |  | 2 | 7.273%
5 | Daniel Gallegos | 3 | 0.5 | 0 |  |  |  |  | 3.5 | 12.73%
6 | Michel Watson | 2.5 | 0.5 | 1.25 |  |  |  |  | 4.25 | 15.45%
SEMESTER TOTAL (hrs) |  | 17.5 | 2.5 | 7.5 | 0 | 0 | 0 | 0 | 27.5 | 100%