## 190 timesheet
CSc 190 WEEKLY TIME and STATUS REPORT | [5 empty] | TEAM NAME_____JBehaving___________________________
Submitted date:__3/4/14_______ | [5 empty] | Submitted by: __Michel Watson_____________________
(Tuesday's class)
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | TOTAL for the Week
1 | Ashley Finger | 2 | 0 | 6 | 0.5 | 0 | 0 | 0 | 8.5
2 | Bai Xiong | 2 | 0 | 2.5 | 0 | 0 | 0 | 0 | 4.5
3 | Cody Lanier | 2.15 | 0 | 1 | 0 | 0 | 0 | 0 | 3.15
4 | Cody Prior | 2 | 0 | 2.15 | 0 | 0 | 0 | 0 | 4.15
5 | Daniel Gallegos | 2 | 0 | 3.5 | 0 | 0 | 0 | 0 | 5.5
6 | Michel Watson | 2.5 | 0 | 4 | 0 | 0 | 0 | 0 | 6.5
WEEKLY TOTAL (hrs) |  | 12.65 | 0 | 19.15 | 0.5 | 0 | 0 | 0 | 32.3
PERCENT COMPLETE |  |  |  | 25% | 0% | 0% | 0% | 0%
*Record times to nearest 15 minutes, representing less than one-hour increments as .25, .50, or .75.
ACCUMULATED TIME SPENT BY EACH TEAM MEMBER: | [9 empty] | Percent of Semester Total
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | SEMESTER TOTAL
1 | Ashley Finger | 7 | 0.5 | 11.5 | 0.5 |  |  |  | 19.5 | 21.08%
2 | Bai Xiong | 10 | 0 | 6.5 | 0 |  |  |  | 16.5 | 17.84%
3 | Cody Lanier | 13.75 | 0.5 | 3.75 | 0 |  |  |  | 18 | 19.46%
4 | Cody Prior | 7 | 0.5 | 2 | 0 |  |  |  | 9.5 | 10.27%
5 | Daniel Gallegos | 8 | 1 | 4.5 | 0 |  |  |  | 13.5 | 14.59%
6 | Michel Watson | 8.5 | 0.5 | 6.5 | 0 |  |  |  | 15.5 | 16.76%
SEMESTER TOTAL (hrs) |  | 54.25 | 3 | 34.75 | 0.5 | 0 | 0 | 0 | 92.5 | 100%