## 190 timesheet
CSc 190 WEEKLY TIME and STATUS REPORT | [5 empty] | TEAM NAME: JBehaving
Submitted date: 3/18/14 | [5 empty] | Submitted by: Michel Watson
(Tuesday's class)
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | TOTAL for the Week
1 | Ashley Finger | 1.5 | 0 | 0 | 4 | 0 | 0 | 0 | 5.5
2 | Bai Xiong | 2.75 | 0 | 0 | 4.25 | 0 | 0 | 0 | 7
3 | Cody Lanier | 2 | 0 | 0 | 4 | 0 | 0.75 | 0 | 6.75
4 | Cody Prior | 1.5 | 0 | 0.5 | 4.25 | 0 | 0 | 0 | 6.25
5 | Daniel Gallegos | 1.5 | 0 | 0 | 3 | 0 | 0 | 0 | 4.5
6 | Michel Watson | 2.5 | 0 | 0.75 | 3.25 | 0 | 0 | 0 | 6.5
WEEKLY TOTAL (hrs) |  | 11.75 | 0 | 1.25 | 22.75 | 0 | 0.75 | 0 | 36.5
PERCENT COMPLETE |  |  |  | 100% | 90% | 0% | 5% | 0%
*Record times to nearest 15 minutes, representing less than one-hour increments as .25, .50, or .75.
ACCUMULATED TIME SPENT BY EACH TEAM MEMBER: | [9 empty] | Percent of Semester Total
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | SEMESTER TOTAL
1 | Ashley Finger | 12 | 0.5 | 10.5 | 9.5 | 0 | 0 | 0 | 32.5 | 19.03%
2 | Bai Xiong | 17.25 | 0.5 | 7 | 7.5 | 0 | 0 | 0 | 32.25 | 18.89%
3 | Cody Lanier | 18.25 | 0.5 | 5.25 | 6.25 | 0 | 0.75 | 0 | 31 | 18.16%
4 | Cody Prior | 11.5 | 0.5 | 3.25 | 7.5 | 0 | 0 | 0 | 22.75 | 13.32%
5 | Daniel Gallegos | 13 | 1 | 5 | 6 | 0 | 0 | 0 | 25 | 14.64%
6 | Michel Watson | 13.5 | 0.5 | 7.5 | 5.75 | 0 | 0 | 0 | 27.25 | 15.96%
SEMESTER TOTAL (hrs) |  | 85.5 | 3.5 | 38.5 | 42.5 | 0 | 0.75 | 0 | 170.75 | 100%