## 190 timesheet
CSc 190 WEEKLY TIME and STATUS REPORT | [5 empty] | TEAM NAME: JBehaving
Submitted date: 4/1/14 | [5 empty] | Submitted by: Michel Watson
(Tuesday's class)
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | TOTAL for the Week
1 | Ashley Finger | 3.25 | 0 | 0 | 0 | 0 | 0 | 0 | 3.25
2 | Bai Xiong | 2.25 | 0 | 0 | 1 | 0 | 0.5 | 0 | 3.75
3 | Cody Lanier | 1.75 | 0 | 1 | 2 | 0 | 0 | 0 | 4.75
4 | Cody Prior | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
5 | Daniel Gallegos | 1.75 | 0 | 0.5 | 0 | 0 | 0.5 | 0 | 2.75
6 | Michel Watson | 2.75 | 0 | 0 | 0.25 | 0 | 0 | 0 | 3
WEEKLY TOTAL (hrs) |  | 13.75 | 0 | 1.5 | 3.25 | 0 | 1 | 0 | 19.5
PERCENT COMPLETE |  |  |  | 100% | 95% | 0% | 6% | 0%
*Record times to nearest 15 minutes, representing less than one-hour increments as .25, .50, or .75.
ACCUMULATED TIME SPENT BY EACH TEAM MEMBER: | [9 empty] | Percent of Semester Total
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | SEMESTER TOTAL
1 | Ashley Finger | 15.25 | 0.5 | 10.5 | 9.5 | 0 | 0 | 0 | 35.75 | 18.82%
2 | Bai Xiong | 19.5 | 0.5 | 7 | 8.5 | 0 | 0.5 | 0 | 36 | 18.95%
3 | Cody Lanier | 20 | 0.5 | 6.25 | 8.25 | 0 | 0.75 | 0 | 35.75 | 18.82%
4 | Cody Prior | 13.5 | 0.5 | 3.25 | 7.5 | 0 | 0 | 0 | 24.75 | 13.03%
5 | Daniel Gallegos | 14.45 | 1 | 5.5 | 6 | 0 | 0.5 | 0 | 27.45 | 14.45%
6 | Michel Watson | 16.25 | 0.5 | 7.5 | 6 | 0 | 0 | 0 | 30.25 | 15.93%
SEMESTER TOTAL (hrs) |  | 98.95 | 3.5 | 40 | 45.75 | 0 | 1.75 | 0 | 189.95 | 100%