## 190 timesheet
CSc 190 WEEKLY TIME and STATUS REPORT | [5 empty] | TEAM NAME: JBehaving
Submitted date: 4/1/14 | [5 empty] | Submitted by: Michel Watson
(Tuesday's class)
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | TOTAL for the Week
1 | Ashley Finger | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
2 | Bai Xiong | 0.25 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.75
3 | Cody Lanier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Cody Prior | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
5 | Daniel Gallegos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Michel Watson | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
WEEKLY TOTAL (hrs) |  | 1.25 | 0 | 0 | 0 | 0.5 | 1 | 0 | 2.75
PERCENT COMPLETE |  |  |  | 100% | 99% | 1% | 7% | 0%
*Record times to nearest 15 minutes, representing less than one-hour increments as .25, .50, or .75.
ACCUMULATED TIME SPENT BY EACH TEAM MEMBER: | [9 empty] | Percent of Semester Total
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | SEMESTER TOTAL
1 | Ashley Finger | 15.75 | 0.5 | 10.5 | 9.5 | 0 | 0 | 0 | 36.25 | 18.81%
2 | Bai Xiong | 19.75 | 0.5 | 7 | 8.5 | 0.5 | 0.5 | 0 | 36.75 | 19.07%
3 | Cody Lanier | 20 | 0.5 | 6.25 | 8.25 | 0 | 0.75 | 0 | 35.75 | 18.55%
4 | Cody Prior | 14 | 0.5 | 3.25 | 7.5 | 0 | 0 | 0 | 25.25 | 13.1%
5 | Daniel Gallegos | 14.45 | 1 | 5.5 | 6 | 0 | 0.5 | 0 | 27.45 | 14.24%
6 | Michel Watson | 16.25 | 0.5 | 7.5 | 6 | 0 | 1 | 0 | 31.25 | 16.22%
SEMESTER TOTAL (hrs) |  | 100.2 | 3.5 | 40 | 45.75 | 0.5 | 2.75 | 0 | 192.7 | 100%