## 190 timesheet
CSc 190 WEEKLY TIME and STATUS REPORT | [5 empty] | TEAM NAME: JBehaving
Submitted date: 3/11/14 | [5 empty] | Submitted by: Michel Watson
(Tuesday's class)
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | TOTAL for the Week
1 | Ashley Finger | 3.5 | 0 | 1 | 5 | 0 | 0 | 0 | 9.5
2 | Bai Xiong | 4.5 | 0 | 0.5 | 3.25 | 0 | 0 | 0 | 8.25
3 | Cody Lanier | 3.5 | 0 | 1.5 | 2.25 | 0 | 0 | 0 | 7.25
4 | Cody Prior | 3 | 0 | 0.75 | 3.25 | 0 | 0 | 0 | 7
5 | Daniel Gallegos | 3.5 | 0 | 0.5 | 3 | 0 | 0 | 0 | 7
6 | Michel Watson | 2.5 | 0 | 0.5 | 2.5 | 0 | 0 | 0 | 5.5
WEEKLY TOTAL (hrs) |  | 20.5 | 0 | 4.75 | 19.25 | 0 | 0 | 0 | 44.5
PERCENT COMPLETE |  |  |  | 100% | 85% | 0% | 0% | 0%
*Record times to nearest 15 minutes, representing less than one-hour increments as .25, .50, or .75.
ACCUMULATED TIME SPENT BY EACH TEAM MEMBER: | [9 empty] | Percent of Semester Total
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | SEMESTER TOTAL
1 | Ashley Finger | 10.5 | 0.5 | 10.5 | 5.5 | 0 | 0 | 0 | 27 | 20.07%
2 | Bai Xiong | 14.5 | 0.5 | 7 | 3.25 | 0 | 0 | 0 | 25.25 | 18.77%
3 | Cody Lanier | 16.25 | 0.5 | 5.25 | 2.25 | 0 | 0 | 0 | 24.25 | 18.03%
4 | Cody Prior | 10 | 0.5 | 2.75 | 3.25 | 0 | 0 | 0 | 16.5 | 12.27%
5 | Daniel Gallegos | 11.5 | 1 | 5 | 3 | 0 | 0 | 0 | 20.5 | 15.24%
6 | Michel Watson | 11 | 0.5 | 7 | 2.5 | 0 | 0 | 0 | 21 | 15.61%
SEMESTER TOTAL (hrs) |  | 73.75 | 3.5 | 37.5 | 19.75 | 0 | 0 | 0 | 134.5 | 100%