## 190 timesheet
CSc 190 WEEKLY TIME and STATUS REPORT | [5 empty] | TEAM NAME: JBehaving
Submitted date: 5/13/14 | [5 empty] | Submitted by: Michel Watson
(Tuesday's class)
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | TOTAL for the Week
1 | Ashley Finger | 3 | 0 | 0 | 0 | 0 | 0 | 1.5 | 4.5
2 | Bai Xiong | 3.5 | 0 | 0 | 0 | 0.25 | 0 | 1.5 | 5.25
3 | Cody Lanier | 4.25 | 0 | 0 | 0 | 0 | 0 | 1.5 | 5.75
4 | Cody Prior | 1.75 | 0 | 0 | 0 | 0 | 5 | 1.5 | 8.25
5 | Daniel Gallegos | 2.5 | 0 | 0 | 0 | 0 | 3 | 1.5 | 7
6 | Michel Watson | 1 | 0 | 0 | 0 | 0 | 0 | 1.5 | 2.5
WEEKLY TOTAL (hrs) |  | 16 | 0 | 0 | 0 | 0.25 | 8 | 9 | 33.25
PERCENT COMPLETE |  |  |  | 100% | 100% | 100% | 100% | 100%
*Record times to nearest 15 minutes, representing less than one-hour increments as .25, .50, or .75.
ACCUMULATED TIME SPENT BY EACH TEAM MEMBER: | [9 empty] | Percent of Semester Total
TEAM MEMBER |  | MGT | LRN | CHARTER | PMP | Feature Wireframes | SRS | Final REQ'Ts Meeting | SEMESTER TOTAL
1 | Ashley Finger | 36.75 | 0.5 | 10.5 | 9.5 | 0 | 25 | 1.5 | 83.75 | 18.96%
2 | Bai Xiong | 39.75 | 0.5 | 7 | 8.5 | 6.75 | 20 | 1.5 | 84 | 19.02%
3 | Cody Lanier | 36 | 0.5 | 6.25 | 8.5 | 0 | 27.25 | 1.5 | 80 | 18.11%
4 | Cody Prior | 28.5 | 0.5 | 3.25 | 8 | 0 | 15.5 | 1.5 | 57.25 | 12.96%
5 | Daniel Gallegos | 31.5 | 1.5 | 5.5 | 6 | 0 | 25.5 | 1.5 | 71.5 | 16.19%
6 | Michel Watson | 31.75 | 0.5 | 7.5 | 6 | 0 | 18 | 1.5 | 65.25 | 14.77%
SEMESTER TOTAL (hrs) |  | 204.25 | 4 | 40 | 46.5 | 6.75 | 131.25 | 9 | 441.75 | 100%